## Index
CCR Analytics — Dashboard Re-platform Matrix
Companion to the 8 May 2026 requirements doc. Page-by-page review of the GMC PowerBI CCR_Analytics_Report, dimension/fact inventory required to refactor it, and a star-schema vs data-product analysis.
Sheets in this workbook
1. Pages_Review | 24 pages in the dashboard. What each shows, dimensions/facts needed to recreate it, and gap classification. Read this first.
2. Dimensions | Master inventory of conformed dimensions required. Status (exists / partial / missing), source system, where it appears, conformance issues.
3. Facts | Master inventory of fact tables required. Grain, measures, source system, dimensions referenced.
4. Data_Products | Opinionated, semantically-baked views built on the dimensions and facts. Each answers a specific question in a fixed shape.
5. Star_vs_Product | Decision framework — when to use a flexible star-schema (semantics declared in BI) vs a packaged data product (semantics baked in).
6. Refactor_Sequence | Build order. Foundation → integration → enrichment → BI front-end. With effort estimates and dependencies.
7. Dimension_Conflicts | Concrete data conflicts identified by inspecting the dashboard screenshots — disagreeing values, conflated concepts, missing semantics, populated-vs-blank inconsistencies. New in v2 of the matrix.
Conventions
Green fill | Capability/data already exists or is mostly there
Yellow fill | Exists but has a gap (mis-shaped, partially populated, conflated)
Red fill | Missing — needs to be built or sourced
Neutral fill | Reference / classification
Blue italic | Source-of-truth field name (page, dimension, fact, product)

## 1_Pages_Review
Pages in CCR_Analytics_Report — what each shows and what it needs
Every page tab visible in the left rail of the dashboard. Status: do we know what it shows from the screens? Page name, observed content, dimensions and facts implied, and what it suggests about additional requirements not yet captured in R1-R11.
# | Page name (left rail) | Page category | What it shows / suggests | Key dimensions implied | Key facts implied | Gap status | Maps to requirement
1 | About | Documentation | Cover page / metadata about the report. Likely contains version, refresh date, contact. Not analytical. | — | — | OK | —
2 | CountryOfRisk View | Counterparty exposure by country | Counterparty exposure aggregated and filterable by country-of-risk dimension. Pre-computed roll-up. Limited drill flexibility. | dim_country, dim_counterparty, dim_tenor_bucket, dim_currency, dim_line | fact_limit, fact_limit_utilization, fact_mtm | Has gaps | R1 (dimensional filter), R4 (parameterised country)
3 | ULT_Parent View | Counterparty exposure by ultimate parent | Roll-up from trading counterparty to ultimate parent. Important for concentration analysis (e.g. all JPMC entities aggregated). | dim_party, dim_party_relationship (parent), dim_tenor_bucket, dim_currency, dim_line | fact_limit, fact_limit_utilization, fact_mtm | Has gaps | R1, R3 (party hierarchy)
4 | Legal Name View | Core working view (counterparty drill) | The central daily working view. CPTY filter (wildcard search) → Limit & Utilisation chart by tenor & currency → CCR Line Details → Trade Details → Party Details. Used for almost every screen George walked through (RBC, Zymer/Bank North Summit, OCC, Alyeska, RBC Capital Markets agent). | dim_party, dim_line, dim_tenor_bucket, dim_currency, dim_product, dim_book, dim_desk, dim_source_system | fact_limit, fact_limit_utilization, fact_mtm, fact_trade, fact_dispute, fact_counterparty_rating | Has gaps | R1, R2, R3, R5, R6, R9, R10, R11 (most central asks)
5 | TDLegal Entity View | Counterparty exposure by TDS booking entity | Same line/utilisation data, sliced by TDS booking entity (TDBK, TDGF, TDEU, TDSC, TDSE, TDSU, TBNA, TCAX). Required because each TDS legal entity has its own credit appetite. | dim_booking_entity, dim_party, dim_tenor_bucket, dim_currency, dim_line | fact_limit, fact_limit_utilization, fact_mtm | Has gaps | R1 (dimensional filter on booking entity)
6 | ExceededONLY View | Breach-only filter view | Pre-filtered view showing only lines where Excess Flag = Y. Operational page for credit officers chasing same-day breaches. | dim_line, dim_party, dim_tenor_bucket (with breach filter) | fact_limit_utilization (filtered to availability < 0) | OK | R10 (excess flag surface)
7 | REPO_Client_Mapping | Repo / SFT mapping reference | Mapping between repo trades and underlying clients. Required because repo trades are often booked under one entity but the credit risk sits with another. SFT-specific reference data. | dim_party, dim_book, dim_product (repo), dim_party_relationship | fact_trade (filtered to SFT), fact_repo_collateral | Missing/new | R5 (SFT context-sensitive columns)
8 | FilterOfReportLines | Operational / data-quality | Likely a filter-tuning or QA page. Used by GMC to validate which lines come through which reports. Operational, not analytical. | — | — | Operational | —
9 | SampleDayLightReport | Daylight exposure | Daylight lines have intra-day limits (HC_DBL, CP_DBL line types end with _DBL). This page shows daylight-specific exposure. | dim_line (filtered to _DBL types), dim_tenor_bucket (intra-day specific) | fact_limit_intraday, fact_limit_utilization_intraday | Has gaps | R1, R5
10 | FXNotionalDeltaPnL_G | Risk attribution — FX (G region) | 6-panel FX risk attribution: Entity View, Top 10 PnL Movement, FX Rate (CCY to USD) % Change as DoD with multi-horizon (D1D, W1W, W2W, MoM, QoQ), Entity CP Code Top Contributor by Line Type, Entity CP PnL CCY Decomposition, CCY Pair View. Computes PnL between London close and Toronto close (G = global / cross-region). | dim_party, dim_booking_entity, dim_currency, dim_line, dim_market_factor, dim_region | fact_sensitivities (FX delta), fact_market_data (FX rates), fact_pnl_attribution | Has gaps | R7 (the prototype to extend to other asset classes)
11 | FXNotionalDeltaPnL_S | Risk attribution — FX (S region) | Likely a sister page to FXNotionalDeltaPnL_G computing PnL between two other regional close times (e.g. NY-Tokyo or session-specific). Same six-panel structure, different time-window parameter. | Same as FXNotionalDeltaPnL_G but with different region pair | Same as FXNotionalDeltaPnL_G | Has gaps | R7
12 | ISRAELI_Notional_Monitoring | Country-specific notional limit page | Hard-coded for Israel. Three Israeli banks (Bank Hapoalim, Bank Leumi, Israel Discount Bank). Strike Notional / Net Notional Limit / Remaining Capacity, split index vs non-index. Daily M2M deltas. Notional breakdown by index ticker (SPTR.IDX, GDDUE15.IDX, NDDUWI.IDX). | dim_country (Israel hard-coded), dim_party, dim_security (index tickers), dim_index_composition | fact_notional_monitoring, fact_country_limit, fact_mtm | Has gaps | R4 (must become parameterised)
13 | Clients Legal Name View | Underlying-client drill (agent decomposition) | For agent counterparties (e.g. Bank North Summit covering 11,840 lines), this view drills past the agent to show individual underlying client legal names. Critical for hedge fund prime brokerage. | dim_party (with role=underlying_client), dim_party_relationship (agent-client), dim_line, dim_tenor_bucket | fact_limit, fact_limit_utilization, fact_mtm | Has gaps | R3 (party hierarchy)
14 | IR/CCS Term TDBK and... | Interest rate / cross-currency swap term view | Interest Rate Swap and Cross-Currency Swap term structure for TDBK booking entity. Likely shows term-by-term DV01 or notional. Truncated name suggests there may be a counterpart "...other entity" page. | dim_product (IRS, CCS), dim_booking_entity, dim_tenor_bucket, dim_currency, dim_market_factor | fact_trade (filtered to IRS/CCS), fact_sensitivities (DV01) | Missing/new | R7 (rates attribution)
15 | TOP 20 NIG Exposures | Non-investment-grade concentration | Top 20 counterparties rated below investment grade (NIG = Non-IG). The slicer "NIG/IG All/Yes/No" on the FX page suggests this is a recurring filter dimension. | dim_party (filtered to NIG), dim_counterparty_rating | fact_counterparty_rating, fact_mtm, fact_limit_utilization | Has gaps | R11 (rating as dimension)
16 | HFund Manager Portfolio | Hedge fund manager view | Aggregates exposure across all funds managed by a single hedge fund manager (e.g. all Citadel funds, all Millennium funds). Concentration view at the manager level above individual fund counterparties. | dim_party (with role=hedge_fund_manager), dim_party_relationship (manager-fund), dim_line | fact_limit_utilization, fact_mtm | Has gaps | R3
17 | Haircut Adj Report | Haircut adjustment / collateral haircut page | Haircut lines (HC_(...) prefix) get their own treatment. Shows the haircut applied to collateral and any adjustments made. The RBC dispute charge of $8.96M sat on a haircut line. | dim_line (filtered to HC_), dim_security, dim_party | fact_collateral_haircut, fact_dispute | Has gaps | R2 (collateral mitigant for default risk), R8
18 | HFund TopView Limit E... | Hedge fund top-view limit/exposure summary | Likely an executive summary across hedge fund counterparties. "TopView" suggests aggregated, headline exposure numbers. | dim_party (filtered to HF), dim_line, dim_tenor_bucket | fact_limit, fact_limit_utilization | Has gaps | —
19 | Hist Treasury Exposure | Historical treasury exposure by country | Properly parameterised country page. Country slicer (Australia, Austria, Azerbaijan, Belgium, Bermuda visible) → drill into 10 sub-categories: Central Bank Treasury, Commercial Bank Fronting Risk, Trade Finance, Treasury, Corporate Treasury, FI Inventory, etc. THIS IS THE PATTERN that R4 (Israeli generalisation) should follow. | dim_country, dim_country_limit_type, dim_party, dim_tenor_bucket | fact_country_limit, fact_country_exposure, fact_mtm | OK | R4 (aspirational pattern)
20 | CAIRO 2 - Facility Expo... | Regulatory — facility exposure | CAIRO is a regulatory reporting framework. CAIRO 2 likely covers facility-level exposure reporting required by regulators (OSFI for Canadian banks). | dim_facility, dim_party, dim_country, dim_regulatory_classification | fact_facility_exposure | Missing/new | Regulatory; not in R1-R11
21 | CAIRO 4 - FI Peer Comparison | Regulatory — FI peer benchmarking | CAIRO 4 covers Financial Institution peer comparison. Likely benchmarks TDS exposure to peer banks for regulatory disclosure. | dim_party (peer banks), dim_regulatory_classification | fact_peer_benchmark, fact_mtm | Missing/new | Regulatory; not in R1-R11
22 | Data Check | Data quality / reconciliation | Almost certainly a control page. Used to validate counts, totals, and reconciliations before report distribution. | — | — | Operational | —
23 | CountryOfRisk View (alt) | Possible duplicate or variant | Possibly a second country view. Without seeing it cannot fully classify. | — | — | Operational | —
24 | IRT Report Lines / DayLight (variants) | Operational variants | Filter and daylight pages may appear in additional variants. The naming pattern across "...Report" pages suggests they are operational rather than analytical. | — | — | Operational | —

## 2_Dimensions
Conformed Dimensions Required
Master inventory of conformed dimensions needed for the refactor. Each dimension is named with what it covers, where the data lives today, what conformance work is needed, and which requirements depend on it.
# | Dimension | Category | Grain / what it identifies | Key attributes | Source system(s) | Today's status | Conformance work required | Requirements served
1 | dim_party | Party master | One row per legal entity (any role) | party_id, legal_name, parent_party_id, ultimate_parent_id, agent_party_id, party_type (CP/issuer/collateral_provider/agent/parent), bloomberg_ticker, internal_flag, country_of_domicile | KYC, SCREAM CP master, Bloomberg, internal CP_CODE registry | Partial | Unify across party-role types. Today only direct trading CPs are in the search. Need to add issuers (from securities ref), collateral providers (from CMOS), guarantors (from KYC). | R1, R3, R11
2 | dim_party_relationship | Party hierarchy | One row per pair of related parties | parent_party_id, child_party_id, relationship_type (parent/subsidiary/guarantor/agent/related_entity/index_constituent), effective_from, effective_to, weight (for index constituents) | KYC, internal hierarchy data, index composition feeds | Missing | Currently no unified relationship table. Hierarchy is implicit in legal name strings ("(BANK NORTH SUMMIT CLIENT)"). Need to extract and conform. | R3
3 | dim_country | Geography | One row per country | country_code (ISO 3166), country_name, region_id, country_of_risk_classification, regulatory_regime_tags (notional_limit_imposed, concentration_threshold), currency_default | Internal reference, Bloomberg, ISO | Exists | Mostly exists. Need to add regulatory_regime_tags so Israeli/notional pages can be parameterised. | R1, R4
4 | dim_country_limit_type | Country sub-classification | One row per country limit category | limit_type_id, limit_type_name (Central Bank Treasury, Commercial Bank Fronting Risk, Trade Finance, Sovereign Direct, Corporate Treasury, FI Inventory, etc.) | Internal credit policy | Exists | Hist Treasury Exposure page already implements this. Just needs to be lifted into a conformed dim. | R4
5 | dim_region | Geography | One row per region | region_code, region_name, market_close_time, region_grouping (Americas, EMEA, APAC) | Internal reference | Exists | Used by FX page (LON / TOR close regions). Conform. | R1, R7
6 | dim_industry | Counterparty classification | One row per industry segment | industry_code (NAICS or GICS), industry_name, parent_industry, internal_TDS_taxonomy | KYC onboarding | Partial / has gaps | INDUSTRY_RATING column exists in Party Details but is partially unpopulated. Need to source full classification from KYC. | R1, R11
7 | dim_desk | Trading organisation | One row per trading desk | desk_code, desk_name, asset_class, location, parent_unit | Internal HR / trading systems | Exists | Largely exists. Conform across pages (currently desk codes vary: ASG, IMDESK, IRD_NYK_NYSOFR, US PRIME EQ SWAP, GED TDBLN EUCEDOPT, LME-AH, XAU-OPT). | R1
8 | dim_booking_entity | TDS legal entities | One row per TDS booking entity | entity_code (TDBK, TDGF, TDEU, TDSC, TDSE, TDSU, TBNA, TCAX, TDAF, TDSU, etc.), entity_name, jurisdiction, regulatory_regime | Internal entity registry | Exists | Codes are visible on every page. Just needs to be a conformed dim. | R1, R5
9 | dim_product | Instrument type | One row per product | product_code, product_name (Equity Swap, Vanilla IRS, FX Forward, CAP, Asian Commodity Option, Commodity Forward, Repo, Cash Collateral, etc.), asset_class, sub_asset_class | Source booking systems (CALYPSO, MUREX, SOPHIS, MUCM, TCIM) | Missing | Today the Deal Type column conflates product, purpose, and lifecycle. Must be split. See R6. | R5, R6, R7
10 | dim_trade_purpose | Booking purpose | One row per purpose | purpose_id, purpose_name (Risk-Taking, Hedge, Initial Margin, Variation Margin, Adjustment-Reversal, Novation) | Derived from booking system metadata | Missing | Does not exist as a field today. IM rows are tagged in 4 separate places (Book=TCIM_IMBOOK, Desk=IMDESK, Deal Type=IM, Deal ID=USDCASH...). Consolidate to one purpose field. | R6
11 | dim_lifecycle_event | Trade lifecycle | One row per event type | event_id, event_name (New, Active, Amended, Cancelled, Adjusted, Novated, Reversed, Expired) | Derived from booking system version field | Missing | Not surfaced today. "Adjustment" is appearing as Deal Type. Move to lifecycle event. | R6
12 | dim_collateral_type | Collateral classification | One row per collateral category | collateral_type_id, collateral_type_name (IM, VM, fee, premium, margin), eligible_assets | CMOS, Colline, CSA agreement reference | Missing | Not in dashboard today. | R2, R6, R8
13 | dim_line | Credit line master | One row per credit line | line_id, line_name, line_type (CONT, C2C, committed, uncommitted, daylight), purpose (CP/HC), owning_booking_entity, governing_policy, product_scope, currency | SCREAM line tables | Partial / has gaps | Lines exist but their type/purpose attributes are encoded in the line name string ("CP_(TDBK)_(RBCM_DBL)"). Parse and structure. | R1, R5, R10
14 | dim_tenor_bucket | Maturity bucket | One row per bucket | bucket_id, bucket_label (N-MTM, 0-3M, 3M-1Y, 1-2Y, 2-5Y, 5-10Y, 10-50Y), bucket_lower_days, bucket_upper_days | Internal credit policy | Exists | Already exists. Just lift into a proper dim. | R1, R9
15 | dim_currency | Currency master | One row per currency | ccy_code (ISO 4217), ccy_name, reporting_priority (USD, CAD primary) | Internal reference, ISO | Exists | Exists. | R1, R9
16 | dim_security | Security / instrument master | One row per security | security_id, ticker, isin, cusip, sedol, issuer_party_id, asset_class, security_country, sector | Securities reference data system, Bloomberg | Missing | Required to support indirect-exposure search via issuer (NVIDIA case). Not in dashboard today. | R3
17 | dim_market_factor | Market data taxonomy | One row per risk factor | factor_id, factor_type (FX rate / equity index / single stock / yield curve point / CDS spread / commodity spot / implied vol point), asset_class, factor_description, factor_currency, factor_region | Bloomberg, Refinitiv, internal market data hub | Missing | FX rates partially present (CCY codes in FX page). Need a conformed factor dim covering all asset classes. | R7
18 | dim_index_composition | Index constituents | One row per (index, constituent, date) | index_id, constituent_security_id, weight_pct, effective_date | Index composition feed (Bloomberg, S&P, MSCI) | Missing | Required for index-implied indirect exposure (NVIDIA via NDX swaps). | R3
19 | dim_csa_agreement | Legal agreements | One row per CSA | agreement_id, counterparty_id, threshold, mta (minimum transfer amount), eligible_collateral_types, governing_law, currency | CMOS, Colline, legal agreement system | Missing | Required for collateral integration. Not in dashboard. | R8
20 | dim_facility | Credit facility | One row per credit facility | facility_id, facility_name, facility_type, parent_party_id, regulatory_classification | SCREAM, regulatory reporting system | Partial / has gaps | Used by CAIRO regulatory pages. Conform. | R1 (CAIRO 2 page)
21 | dim_source_system | Data lineage | One row per source booking system | source_system_code (CALYPSO, MUREX, SOPHIS, MUCM, TCIM, MANUAL), source_system_name, asset_class_focus, data_quality_tier | Internal IT registry | Partial / has gaps | Source System column visible on every Trade Details panel. Conform. | R5
22 | dim_counterparty_rating | Credit ratings (slowly changing) | One row per (party, rating_source, effective_date) | party_id, rating_source (Internal, Moody's, S&P, Fitch), rating_value (1A through 5C internal; AAA-D external), effective_from, effective_to | Internal credit committee, Moody's, S&P feeds | Partial | Ratings shown on Party Details (INTERNAL_RATING, MOODYS_RATING, SANDP_RATING) but only as snapshots. Add history. | R11

## 3_Facts
Fact Tables Required
Master inventory of fact tables. Each fact has a clear grain (one row per what), measures, and dimensions referenced. Source system says where the data originates today.
# | Fact | Grain | Measures | Dimensions referenced | Source system(s) | Today's status | Notes | Requirements served
1 | fact_limit | One row per (line × tenor_bucket × currency × value_date) | approved_limit, currency, max_usage_historical | dim_line, dim_tenor_bucket, dim_currency, dim_party (via line) | SCREAM line tables | Partial / has gaps | Available via SCREAM canned reports today. Need direct table access. | R1, R9, R10
2 | fact_limit_utilization | One row per (line × tenor_bucket × currency × value_date) | utilization_amount, availability (= limit - utilization), excess_flag, max_usage_in_period | dim_line, dim_tenor_bucket, dim_currency, dim_party (via line) | SCREAM utilisation tables | Partial / has gaps | Same as fact_limit. Excess Flag is the breach trigger. | R1, R9, R10
3 | fact_limit_intraday | One row per (line × intraday_window × currency) | daylight_limit, intraday_peak_utilization, intraday_close_utilization | dim_line (filtered to _DBL), dim_currency, dim_party | SCREAM daylight feed | Partial / has gaps | Specific to daylight (DBL) lines. Drives SampleDayLightReport. | —
4 | fact_trade | One row per (trade × value_date) — daily snapshot | notional, principal_1, principal_2, principal_1_currency, principal_2_currency, c2c_charge, deal_m2m, deal_m2m_currency, years_to_maturity | dim_party, dim_book, dim_line, dim_product, dim_trade_purpose, dim_lifecycle_event, dim_collateral_type, dim_desk, dim_source_system, dim_currency | SCREAM trade ledger; underlying booking systems (CALYPSO, MUREX, SOPHIS, MUCM, TCIM, MANUAL) | Partial / has gaps | Today flat — needs to be split so attributes don't conflate. Wide-table or normalised satellite design (R5, R6). | R1, R5, R6
5 | fact_mtm | One row per (trade × value_date) | mtm_value, mtm_currency, mtm_change_dod, gross_mtm_impact | dim_party (via trade), dim_currency, dim_book | Valuation engines (RCAPS, XVALA); upstream booking systems | Partial | Currently embedded in fact_trade (Deal M2M column). Promote to first-class fact for cross-counterparty queries. | R2
6 | fact_collateral_balance | One row per (counterparty × agreement × asset × value_date) | gross_collateral_value, haircut_pct, net_collateral_value, posting_party (TDS or counterparty), collateral_type (IM/VM) | dim_party (posting), dim_csa_agreement, dim_security (asset), dim_collateral_type, dim_currency | CMOS, Colline | Missing | Not in dashboard. Required for default risk computation (R2) and indirect exposure (R3). | R2, R3, R8
7 | fact_margin_call | One row per margin call event | called_amount, currency, direction (issued/received), call_time, expected_settlement, actual_settlement, status (open/settled/disputed) | dim_party, dim_csa_agreement | CMOS, Colline | Missing | Email digest only today. Bring inline. | R8
8 | fact_margin_dispute | One row per dispute | disputed_amount, currency, reason_code, age_days, resolution_status, opened_date, resolved_date | dim_party, dim_csa_agreement | CMOS, Colline | Partial / has gaps | Visible as "Dispute Charge" column on CCR Line Details (RBC $8.96M). Promote to fact. | R2, R8
9 | fact_pfe | One row per (counterparty or netting_set × horizon × confidence × value_date) | pfe_value, stressed_pfe_value, peak_pfe, expected_exposure (EE) | dim_party, dim_horizon, dim_confidence_level | RCS | Missing | Not in dashboard. Required for default risk (R2). | R2
10 | fact_sensitivities | One row per (trade × market_factor × sensitivity_type × value_date) | sensitivity_value, sensitivity_currency | dim_party (via trade), dim_market_factor, dim_book, dim_currency | Valuation engines (RCAPS, XVALA), source systems (CALYPSO, MUREX, SOPHIS), SENTOR | Partial | FX deltas appear to flow through (FX page works). Equity, Rates, Credit, Commodity sensitivities not surfaced. Critical for R7. | R7
11 | fact_market_data | One row per (factor × date) — daily; intraday for fast factors | eod_value, intraday_value, change_dod, change_wow, change_mom, change_qoq, change_d1d, change_w1w, change_w2w | dim_market_factor, dim_currency, dim_region | Bloomberg, Refinitiv, internal market data hub | Partial | FX rates partially present (visible in FX heat map: CAD, JPY, GBP, EUR, KRW, RON, NOK, ZAR with multi-horizon changes). Need full domain coverage. | R7
12 | fact_pnl_attribution | Derived: one row per (trade × factor × value_date) | pnl_impact = sensitivity × market_move, attribution_currency | dim_party, dim_market_factor, dim_book, dim_desk, dim_currency | Computed in Gold layer from fact_sensitivities × fact_market_data | Partial | FX page implements this for FX. Generalise to all asset classes. | R7
13 | fact_country_limit | One row per (country × limit_type × value_date) | gross_max_exposure, current_usage, available_capacity, by_tenor_bucket | dim_country, dim_country_limit_type, dim_tenor_bucket | SCREAM country limit tables | Partial / has gaps | Drives Hist Treasury Exposure page. Conform. | R4
14 | fact_notional_monitoring | One row per (country × party × asset_class × value_date) | strike_notional, net_notional_limit, remaining_capacity, daily_m2m_delta, m2m_t0, m2m_t-1, index_vs_non_index_split | dim_country, dim_party, dim_security (index ticker), dim_asset_class | SCREAM notional monitoring extracts | Partial / has gaps | Drives Israeli page. Generalise. | R4
15 | fact_counterparty_rating | One row per (party × rating_source × effective_date) | rating_value, rating_outlook, watch_status | dim_party, dim_counterparty_rating | Internal credit committee, Moody's, S&P feeds | Partial / has gaps | Snapshot only today. Add history for time-travel queries. | R11
16 | fact_facility_exposure | One row per (facility × counterparty × value_date) | facility_limit, facility_drawdown, facility_committed, facility_uncommitted | dim_facility, dim_party, dim_country | SCREAM, regulatory reporting | Partial / has gaps | Drives CAIRO 2 regulatory page. | Regulatory
17 | fact_collateral_haircut | One row per (collateral_position × value_date) | pre_haircut_value, applied_haircut_pct, post_haircut_value, haircut_adjustment | dim_security, dim_party, dim_collateral_type | CMOS, Colline, internal haircut policy | Missing | Drives Haircut Adj Report. | R2, R8
18 | fact_repo_collateral | One row per (repo_trade × leg × value_date) | repo_notional, repo_rate, collateral_security_id, collateral_value, haircut | dim_party, dim_security, dim_book | CALYPSO repo book; SCREAM | Missing | SFT-specific. Drives REPO_Client_Mapping. | R5
19 | fact_indirect_exposure | Derived: one row per (party × path × value_date) | indirect_exposure_value, path_type (collateral_provider, issuer, parent, related, agent, index_constituent), source_record_ref | dim_party (target), dim_party (intermediary), dim_security, dim_party_relationship | Computed in Gold layer joining fact_collateral_balance + dim_security + dim_party_relationship | Missing | Required for NVIDIA-style indirect search. | R3
20 | fact_default_risk | Derived: one row per (counterparty × value_date) | gross_mtm, collateral_haircut_adjusted, net_exposure, pfe_addon, default_risk_exposure | dim_party, dim_currency | Computed in Gold layer from fact_mtm + fact_collateral_balance + fact_pfe | Missing | Required for "default risk" headline in R2. | R2

## 4_Data_Products
Data Products — Opinionated, Semantic Views
A data product is a view built on top of dimensions and facts where the semantic interpretation is BAKED IN. Less flexible than a star schema (the consumer can't re-cut it freely), but the question it answers is unambiguous and consistent across consumers. Below: candidate data products derived from the page-by-page review.
# | Data product | Question it answers | Built on (dims) | Built on (facts) | Baked-in semantics (opinions) | Replaces / serves dashboard pages | Refresh cadence
1 | dp_counterparty_exposure_summary | For any counterparty, what is my full exposure picture today? (Limits, MTM, direct, indirect, default risk — all five concepts in one view) | dim_party, dim_party_relationship, dim_line, dim_tenor_bucket, dim_currency | fact_limit, fact_limit_utilization, fact_mtm, fact_collateral_balance, fact_pfe, fact_indirect_exposure, fact_default_risk | Default Risk is computed as gross_mtm − collateral_haircut_adjusted + pfe_addon. Direct vs indirect is path-classified. Reporting currency = USD with CAD secondary. PFE horizon = 1 year, 95th percentile. | Legal Name View, ULT_Parent View, TDLegal Entity View, Clients Legal Name View, ExceededONLY View | Daily T+0 (intra-day for breaches)
2 | dp_country_risk_monitoring | For any country, what is the regulatory exposure picture? (Limits by sub-category, notional monitoring where required, concentration metrics) | dim_country, dim_country_limit_type, dim_party, dim_security (indices), dim_index_composition | fact_country_limit, fact_country_exposure, fact_notional_monitoring, fact_mtm | Country sub-categories follow the Hist Treasury Exposure taxonomy (Central Bank / Commercial Bank / Trade Finance / etc.). Notional monitoring activates only for countries flagged with regulatory_regime_tag=notional_limit_imposed. Index decomposition uses dim_index_composition with daily refresh. | CountryOfRisk View, Hist Treasury Exposure, ISRAELI_Notional_Monitoring | Daily
3 | dp_risk_movement_attribution | For any asset class, where did today's risk move and which counterparties drove it? | dim_party, dim_booking_entity, dim_market_factor, dim_currency, dim_region, dim_book, dim_desk | fact_sensitivities, fact_market_data, fact_pnl_attribution | PnL impact = sensitivity × market_move, computed once and aggregated up. "Top contributor" defined as ranked by absolute dollar impact, not by volume. Multi-horizon comparison (DoD, W1W, W2W, MoM, QoQ) standardised. Time-window is region-pair-based (LON close vs TOR close, etc.). | FXNotionalDeltaPnL_G, FXNotionalDeltaPnL_S; replicates of same for Equities, Rates, Credit, Commodities | Multiple times daily (region-close-to-region-close)
4 | dp_collateral_and_margin_calls | What's the collateral picture today? Margin call activity, disputes, expected vs actual settlement. | dim_party, dim_csa_agreement, dim_collateral_type, dim_security | fact_collateral_balance, fact_margin_call, fact_margin_dispute, fact_collateral_haircut | Margin call status colour-coded by the Daskalov traffic-light convention. DXY correlation pre-computed and joined. Dispute aging buckets: 0-7d, 8-30d, 31-90d, 90d+. Haircut sourced from internal policy, not externally. | Replaces the daily margin call email; serves Haircut Adj Report and integrates collateral into Legal Name View | Daily T+0; intraday for active calls
5 | dp_indirect_party_exposure | When I search a party (NVIDIA, JPMC parent), what indirect paths expose me to that party? | dim_party, dim_party_relationship, dim_security, dim_index_composition | fact_collateral_balance (provider path), fact_trade (issuer path via securities), fact_indirect_exposure | Path types are enumerated: collateral_provider, issuer (of held collateral), parent, related, agent, index_constituent. Index-constituent path uses latest dim_index_composition weights. Indirect exposure is summed across paths but flagged by path type so a user can drill down. | Adds new functionality. No current page does this — fundamentally new capability. | Daily
6 | dp_breach_and_dispute_alerting | What's breached or disputed today and where? | dim_party, dim_line, dim_tenor_bucket, dim_country, dim_csa_agreement | fact_limit_utilization (filtered to availability < 0), fact_margin_dispute (status=open), fact_collateral_balance (shortfall) | Severity ranked by absolute dollar exposure × counterparty rating tier. Breach types pre-classified (line breach, country breach, agreement breach). Aging tracked. | ExceededONLY View, dispute charges in CCR Line Details | Intra-day
7 | dp_hedge_fund_concentration | Across all my hedge fund counterparties (and managers), where are the concentrations and what's rated NIG? | dim_party (with role=HF), dim_party_relationship (manager-fund), dim_industry, dim_counterparty_rating | fact_limit_utilization, fact_mtm, fact_counterparty_rating | Investment grade boundary defined as internal_rating ≤ 3C. NIG flag derived. Manager roll-up follows dim_party_relationship parent_party_id. Top 20 cut by absolute exposure × rating tier. | HFund Manager Portfolio, HFund TopView Limit, TOP 20 NIG Exposures | Daily
8 | dp_regulatory_reporting | CAIRO 2 facility exposure and CAIRO 4 peer comparison views — regulatory deliverables | dim_facility, dim_party, dim_country, dim_regulatory_classification | fact_facility_exposure, fact_peer_benchmark | Output format is locked to OSFI/regulator template. Aggregation rules follow CAR (Capital Adequacy Requirement) guidelines. Frozen each month-end for submission. | CAIRO 2 - Facility Exposure, CAIRO 4 - FI Peer Comparison | Monthly (regulatory cycle)
9 | dp_repo_sft_exposure | Repo and securities-financing-transaction exposure with proper client mapping | dim_party (trading + underlying client), dim_party_relationship (repo agent-client), dim_security (collateral), dim_book | fact_trade (filtered to SFT), fact_repo_collateral | SFT-specific column set used. Trading party vs ultimate-credit-risk party split clearly. Tri-party repo agent relationships modeled. | REPO_Client_Mapping; serves Trade Details when SFT in scope | Daily
10 | dp_intraday_daylight | Intra-day exposure spikes and daylight line consumption | dim_line (daylight DBL types), dim_party, dim_tenor_bucket (intraday) | fact_limit_intraday, fact_limit_utilization_intraday | Daylight peak measured per intra-day window. Reset at end of day. Different from overnight exposure conceptually. | SampleDayLightReport | Multiple times intraday

## 5_Star_vs_Product
Star Schema vs Data Product — When to use which
Two complementary approaches sitting on top of the same conformed dimensions and facts. Star schema = facts + dims declared, semantics applied AT QUERY TIME by the BI tool (open, flexible, requires consumer to know the model). Data product = a view where the semantic decisions are baked in already (less flexible, but every consumer gets the same answer). Most enterprise CCR analytics layers need both.
Comparison
Aspect | Star schema (semantics declared in BI) | Data product (semantics baked in)
What it is | Conformed dimensions + facts exposed as a queryable model. Joins, filters, aggregations applied by the consumer. Power BI / Strategy / Tableau adds business logic on top. | A pre-shaped view answering a specific question. Joins, filters, derived measures, segmentation rules already applied. Consumer queries it like a flat table.
Flexibility | High. Same model serves dozens of questions because the consumer composes them. | Low. The product answers ONE question (or a tightly-related family). Different questions need different products.
Consumer skill required | BI-literate user. Must understand relationships, grain, and filter context. | Anyone. The shape tells you exactly what you can ask.
Consistency across consumers | Risk of inconsistency. Two analysts can build the same dashboard with subtly different filter logic and get different numbers. | High. Everyone querying the same product gets the same answer. Single source of truth for that question.
Semantic ownership | Distributed. Each BI report's author bakes the semantics into their queries / DAX / measures. | Centralised. The product owner makes the semantic decisions once.
Best for | Exploration. Ad-hoc analysis. Cases where the question isn't fully formed. Self-service analytics for power users. | Production reporting. Regulatory deliverables. Cross-team consumption where consistent answers matter. Use cases with clear, repeated questions.
Effort to add a new question | Low. Build a new query against the existing model. | High. Build a new product (or extend an existing one carefully).
Effort to change semantic rules | Medium-high. Every report using that semantic needs to be updated. | Low. Update the product once; all consumers automatically pick up the change.
Risk of mis-use | High. Wrong joins, wrong grain, double-counting are all easy. | Low. Hard to misuse a single-purpose view.
Refresh / latency | Live model. Whatever cadence the underlying facts refresh. | Materialized at product cadence (daily, intra-day). Trade-off: stale-by-product-cadence vs. computed-at-query-time.
In Databricks / Unity Catalog | Silver-layer dims + facts exposed via Unity Catalog. BI queries them directly. | Gold-layer materialized views or tables. Consumers query the product, not the underlying facts.
Where each CCR use case fits
Use case | Star schema or Data product? | Reasoning
George's "tabbed dimensional navigation" (R1) | Star schema | Open-ended exploration. He explicitly wants to compose filters in any order. Cannot pre-bake every possible combination.
"Show contingent lines running hot in 1-2yr bucket" (R1 litmus test) | Star schema | Ad-hoc question that should be one filter chain away. Pre-baking it would only solve this one question.
Five-way exposure decomposition (R2) | Data product | Same five concepts, same definition, every consumer. Default Risk computation is opinionated — must be consistent. Wrap as dp_counterparty_exposure_summary.
Indirect party search NVIDIA-style (R3) | Data product | Path classification logic is opinionated. The "what counts as indirect" decisions need to be made once (collateral provider, issuer, parent, etc.). Wrap as dp_indirect_party_exposure.
Country-of-risk parameterised view (R4) | Data product | Same shape, parameterised by country. Hist Treasury Exposure is already this pattern. dp_country_risk_monitoring.
Context-sensitive columns (R5) | Star schema | BI-tool concern. The model exposes everything; the BI layer hides what isn't relevant for the trade type in scope.
IM/Adjustment/Deal Type fix (R6) | Star schema (model fix) | Conformance issue, not a product issue. Fix at the dim level (split into product, purpose, lifecycle dims).
Risk movement attribution (R7) | Data product | Heavily opinionated: how to attribute, what counts as a "factor", how to bucket horizons, how to handle vega vs delta. dp_risk_movement_attribution.
Margin call digest replacing email (R8) | Data product | Pre-shaped view with traffic-light, DXY correlation, expected vs actual already computed. dp_collateral_and_margin_calls.
Tenor-bucketed limits in dual currencies (R9) | Star schema | Currency is a dimension, not a value. Once dim_tenor_bucket and dim_currency are properly conformed, any BI tool slices it correctly.
Excess flag / breach surface (R10) | Both | Star schema for ad-hoc breach queries; Data product (dp_breach_and_dispute_alerting) for the operational morning-of breach review.
Party Details as filterable dims (R11) | Star schema | Make the attributes proper dims. Industry, rating, country become slicers. The BI tool composes the rest.
CAIRO regulatory reporting | Data product | Output format is locked by regulator. Hard-shape it as a product to guarantee consistency and prevent ad-hoc deviations.
Daily breach review (operational) | Data product | Same view every morning. Bake it.
"Why did exposure jump for this counterparty?" | Star schema | Ad-hoc investigative work. Needs free composition of dimensions.

## 6_Refactor_Sequence
Refactor Build Sequence
Recommended order. Each step lists the deliverable, what it depends on, and which dashboard pages and George requirements it unlocks. Effort is rough relative sizing; calibrate against actual team capacity.
Phase | Step | Deliverable | Depends on | Unlocks (pages) | Unlocks (requirements) | Effort
Phase 1 — Foundation | 1 | Conformed dimensions in Databricks Silver: dim_party, dim_country, dim_country_limit_type, dim_region, dim_booking_entity, dim_currency, dim_tenor_bucket, dim_line, dim_desk | Source-system access (KYC, internal registries) | All | Foundation for R1, R4, R9, R11 | L (large)
Phase 1 — Foundation | 2 | SCREAM source-table pipeline: fact_limit, fact_limit_utilization, fact_mtm, fact_trade (initially flat). Replace canned-report dependency. | Step 1; SCREAM source-table access | Legal Name View, ULT_Parent View, TDLegal Entity View, ExceededONLY View, CountryOfRisk View | R1 (foundation), R10 | L (large)
Phase 1 — Foundation | 3 | Re-platform Legal Name View on the new model. Tabbed dimensional navigation (R1) implemented in BI. | Steps 1-2 | Legal Name View | R1 fully | M (medium)
Phase 2 — Trade taxonomy | 4 | Conformance fix for IM/Adjustment/Deal Type: split into dim_product, dim_trade_purpose, dim_lifecycle_event, dim_collateral_type. Rebuild fact_trade with proper FKs. | Step 1 | Legal Name View, Trade Details across all pages | R5, R6 | M (medium)
Phase 2 — Trade taxonomy | 5 | Source-system enrichment for trade attributes (CALYPSO, MUREX, SOPHIS, MUCM, TCIM, MANUAL). Wider trade fact / satellite tables. | Step 4 | Legal Name View, REPO_Client_Mapping, IR/CCS Term TDBK | R5 | M (medium)
Phase 3 — Collateral integration | 6 | CMOS / Colline pipeline: fact_collateral_balance, fact_margin_call, fact_margin_dispute, fact_collateral_haircut, dim_csa_agreement, dim_collateral_type | Step 1 | Haircut Adj Report, integrates into Legal Name View | R8 (the email replacement); enables R2 (default risk) | L (large)
Phase 3 — Collateral integration | 7 | Data product: dp_collateral_and_margin_calls. Replaces the daily email digest with a live, drillable view. | Step 6 | Replaces email; new product | R8 fully | M (medium)
Phase 4 — Default risk and indirect exposure | 8 | Conformed dim_security with issuer linkages; dim_party_relationship; dim_index_composition. Securities reference data pipeline. | Step 1 | Enables NVIDIA-style search | R3 | M (medium)
Phase 4 — Default risk and indirect exposure | 9 | fact_pfe pipeline (RCS source). Computed Gold view fact_default_risk = gross_mtm - collateral_haircut + pfe_addon. | Steps 6, 8 | — | R2 | M (medium)
Phase 4 — Default risk and indirect exposure | 10 | Data products: dp_counterparty_exposure_summary (the 5-way decomposition); dp_indirect_party_exposure (NVIDIA path search). | Steps 8, 9 | Replaces Current Exposure tile across Legal Name View etc. | R2, R3 fully | L (large)
Phase 5 — Country and regulatory generalisation | 11 | Generalise country-of-risk page: lift Hist Treasury Exposure pattern; collapse Israeli page into parameterised dp_country_risk_monitoring. Add fact_country_limit, fact_notional_monitoring as conformed. | Step 1; for ISRAELI also dim_index_composition | CountryOfRisk View, ISRAELI_Notional_Monitoring, Hist Treasury Exposure | R4 | M (medium)
Phase 5 — Country and regulatory generalisation | 12 | CAIRO regulatory data products. fact_facility_exposure, fact_peer_benchmark. | Step 1 | CAIRO 2 Facility Exposure, CAIRO 4 FI Peer Comparison | (Regulatory; not in R1-R11) | M (medium)
Phase 6 — Sensitivities & risk movement attribution | 13 | fact_sensitivities pipeline (RCAPS, XVALA, source systems, SENTOR). Conformed dim_market_factor. | Step 1 | FX page on new model; foundation for other asset classes | R7 (foundation) | L (large)
Phase 6 — Sensitivities & risk movement attribution | 14 | fact_market_data pipeline from Bloomberg / Refinitiv / internal hub. Multi-horizon (DoD, W1W, W2W, MoM, QoQ) pre-computed. | Step 13 | FX, Equity, Rates, Credit, Commodity attribution pages | R7 | M (medium)
Phase 6 — Sensitivities & risk movement attribution | 15 | Data product: dp_risk_movement_attribution. Replicate FX page paradigm for Equities, Rates, Credit, Commodities. | Steps 13, 14 | FXNotionalDeltaPnL_G, FXNotionalDeltaPnL_S, plus 4 new pages | R7 fully | L (large)
Phase 7 — Specialised products | 16 | dp_hedge_fund_concentration (HFund Manager Portfolio, HFund TopView Limit, TOP 20 NIG Exposures); dp_repo_sft_exposure (REPO_Client_Mapping) | Steps 1-5 | HFund pages, REPO mapping, NIG view | R3, R5, R11 | M (medium)
Phase 7 — Specialised products | 17 | dp_breach_and_dispute_alerting; dp_intraday_daylight | Steps 2, 6 | ExceededONLY View, SampleDayLightReport | R10 | S (small)
Phase 8 — BI front-end polish | 18 | Tabbed dimensional navigation; column picker; context-sensitive columns; saved user preferences. Per BI tool (Power BI, Strategy, both). | All preceding | All | R1, R5 final delivery | M (medium)

## 7_Dimension_Conflicts
Dimension Data Conflicts — Visible in Screenshots
Concrete data conflicts identified by inspecting the dashboard screenshots carefully. Each row names the dimension/field affected, the specific conflict, the screenshot evidence, severity, and what needs to happen to resolve it. Read alongside Sheet 2_Dimensions for the master inventory.
Severity legend
Critical | Data integrity issue — values disagree, are missing where they should be present, or carry meaning the user cannot derive
Ambiguous | Field is populated but semantics are unclear, or representation conflates concepts
Documented | Behaviour is a known design choice but worth flagging because it surprises new users
# | Dimension / field | Conflict | Evidence (screenshot) | Observed values | Severity | Why it matters | Resolution required
1 | Deal Type (dim_product) | Column conflates three different concepts: instrument type, booking purpose, lifecycle event | Alyeska Master Fund Trade Details (IMG_6260) | Equity Swap, Equity Swap, Equity Swap, Equity Swap, IM (the IM row sits alongside Equity Swap rows in the same column) | Critical | Cannot answer "show me my equity-swap-related exposure including the IM that backs it" because IM rows do not carry the underlying product. The IM row identifies itself as IM-related 4 ways (Book=TCIM_IMBOOK, Desk=IMDESK, Deal ID=USDCASH00006D1, Deal Type=IM) and never names the product it collateralises. | Split into dim_product (Cash Collateral for IM, Equity Swap for OTC), dim_trade_purpose (Risk-Taking vs Initial Margin), dim_collateral_type (IM/VM). Carry underlying_portfolio_id on IM rows.
2 | Deal Type (dim_product) | Column carries lifecycle event values like "Adjustment", losing the underlying product | Zymer Gjonbalaj Trade Details (IMG_6249/6252) | Adjustment, Adjustment, Adjustment, Adjustment, Adjustment — all 5 visible rows. Book column carries MANUAL_ASG, MANUAL_GED TDBLN EUCEDOPT, MANUAL_LME-AH instead | Critical | Manual adjustments are bookings against underlying trades but the underlying trade is invisible. "Adjustment" is a lifecycle action, not a product. Without parent_trade_id, the adjustment cannot be reconciled to what it adjusts. | dim_lifecycle_event = Adjustment; dim_product = the underlying product (inherited); add parent_trade_id pointer to the original trade.
3 | Deal Type — Trade Details column shape | Column set changes per counterparty type — the Deal Type column is present for some, absent for others | OCC Trade Details (IMG_6257) vs RBC/Alyeska Trade Details (IMG_6248/6260) | OCC view: columns are Desk, Trade Date, Maturity Date, Source System, Version, Years To Maturity, Deal M2M Currency, Deal M2M, Principal 1, Principal 1 Currency, Principal 2, Principal 2 Currency, C2C Charge, C2C Charge Cur — NO Deal Type column. RBC/Alyeska view: Value Date, Book, C Line, Counterparty Code, Deal ID, Deal Type, Desk, ... — HAS Deal Type column | Critical | Same dashboard page (Legal Name View) renders different column sets for different counterparties. Users cannot rely on column position. Suggests OCC trades are SFT/cleared and have a fundamentally different shape — confirming R5 (context-sensitive columns). | Conformed dim_product taxonomy plus per-asset-class trade-fact satellites. UI metadata indicating which columns are relevant per asset class. R5.
4 | dim_party_relationship — agent vs underlying client | Agent legal entity has approved lines but no trades; underlying clients carry the trades but appear under the agent name | RBC Capital Markets LLC AS AGENT FOR ROYAL BANK OF (IMG_6256) vs Zymer Gjonbalaj/Bank North Summit (IMG_6249) | RBC Capital Markets agent: 2 approved lines ($100,000,001 total availability), Trade Details panel EMPTY (zero rows). Zymer Gjonbalaj: 11,840 lines aggregated under the agent name — the 5 visible Trade Details rows have Counterparty Codes pointing to 5 different underlying clients (FNFC_C2C, MPFN_C2C, MGDN_C2C, TIST_C2C ×2) | Critical | There is no dim_party_relationship surfaced. The "agent" relationship is encoded in the LEGAL_NAME string ("(BANK NORTH SUMMIT CLIENT)", "AS AGENT FOR ...") and the user has to parse it. Underlying clients are not properly drillable. | Build dim_party_relationship with relationship_type=agent. Extract from LEGAL_NAME strings and KYC. Surface the agent → underlying-client hierarchy as a proper dimension.
5 | Counterparty Code naming convention | Same counterparty appears under multiple codes representing different TDS booking entities | OCC Lines (IMG_6257) | Three lines for OCC: CP_(TDAF)_(OPCL_EBL), CP_(TDSC)_(OPCL_EBL), CP_(TDSU)_(OPCL_EBL) — same counterparty (OPCL = OCC), three different TDS legal entities (TDAF, TDSC, TDSU). Party Details shows OPCL_BSB, OPCL_DBL, OPCL_EBL — three different CP_CODE values for the same legal name "THE OPTIONS CLEARING CORPORATION-USA" | Documented | This is expected behaviour — credit lines are issued per (TDS booking entity, external CPTY) pair, so the same external CPTY gets multiple CP_CODEs. But the user has to know this; the model does not express it cleanly. | dim_counterparty with external_party_id (the OCC concept) separated from booking_relationship_id (the per-entity line). Promotes a many-to-one relationship that is currently flattened.
6 | dim_line — line metadata encoded in the line name string | Line type, purpose, owning entity, and counterparty are all packed into the line name as a coded string | Across all CCR Line Details panels | Examples: CP_(TDBK)_(RBCM_DBL) — Counterparty line, TDBK entity, RBCM counterparty, Daylight type. HC_(TDBK)_(RBCM) — Haircut line, TDBK entity, RBCM. CP_(TDSC)_(BAN2_EBL) — CP line, TDSC entity, BAN2 counterparty, EBL line subtype. CP_(TDBK)_(GAMP_C2C) — CP line, TDBK, GAMP, C2C subtype. | Ambiguous | Information is present but the user (or any downstream system) has to parse a regex to get at it. Cannot filter "show me all _DBL lines across all counterparties" without string parsing. Conflates 4 attributes into 1 string. | Parse line name into dim_line attributes: line_purpose (CP/HC), owning_booking_entity (TDBK/TDSC/etc.), counterparty_code (RBCM/BAN2/etc.), line_subtype (_DBL/_C2C/_EBL/_CONT). Keep original line_name as a key.
7 | External ratings — MOODYS_RATING / SANDP_RATING | Inconsistent population across counterparties | RBC (IMG_6255), Alyeska (IMG_6260), OCC (IMG_6257), RBC Agent (IMG_6256) | RBC: MOODYS=AA, SANDP=NR across 3 entity rows. Alyeska: MOODYS=blank, SANDP=blank. OCC: MOODYS=NR, SANDP=NR. RBC Capital Markets agent: MOODYS=NR, SANDP=NR. Internal Rating populated for all. | Ambiguous | Three different "no rating" representations: blank (Alyeska), NR (OCC, agent), and populated (RBC). The user cannot tell whether "NR" means Not Rated by the agency, Not Retrieved from the feed, or Not Reported in our reference data. RBC has S&P NR which is unlikely in reality — RBC has a published S&P rating. | Distinguish NR (Not Rated by agency) from NULL (not retrieved). Validate the external rating feed — RBC having S&P NR is likely a data gap, not an actual rating absence.
8 | Worst Rating Of Associated Clients | Single rating per line but for agent blocks, the underlying clients have different ratings | Zymer Gjonbalaj CCR Line Details (IMG_6249) | CP_(TDSC)_(BAN2_EBL) shows Worst Rating = 1A (excellent). CP_(TDBK)_(GAMP_C2C) shows Worst Rating = 5C (very weak). Both lines flagged Y (breach). But the chart says "11,840 Lines Aggregated" — the rating is a roll-up across many underlying clients per line, and the user does not see the distribution. | Ambiguous | The single-column rating hides the distribution. A 1A worst-rated line means every underlying client is 1A. A 5C worst-rated line could be all 5C or one 5C among many better. Cannot tell. | Surface rating distribution per line (count by rating bucket, weighted-average exposure by rating). Or drill from agent-block line to underlying-client ratings.
9 | COUNTRY_RISK on Party Details | CAN code on a Sydney-listed legal entity | RBC Party Details (IMG_6255) | RB2C_SDY — ROYAL BANK OF CANADA-SDY (REG VM CSA), BLOOMBERG_TICKER=69229Z AU (Sydney/Australian listing), COUNTRY_RISK=CAN | Documented | COUNTRY_RISK is the banks assessed country of risk, not country of legal domicile or country of listing. For RBC Sydney branch this is genuinely CAN (the credit risk traces back to parent RBC, regardless of where the local branch operates). But a user could easily misread CAN as a data error. | No data change needed. Document the semantic: COUNTRY_RISK = country of credit risk assessment, separate from country_of_domicile and country_of_listing dim attributes.
10 | INDUSTRY_RATING population | Inconsistent population — some counterparties have it, others do not | RBC (IMG_6255), Alyeska (IMG_6260), OCC (IMG_6257), Zymer (IMG_6249) | RBC: INDUSTRY_RATING = 3 (populated). OCC: INDUSTRY_RATING = 3 (populated). Alyeska: INDUSTRY_RATING = 5 (populated). Zymer Party Details visible at bottom — INDUSTRY_RATING column appears empty for both rows (11FW_TOR, 1TDN_USA). | Ambiguous | Not entirely missing as the v1 review concluded — it is populated for FI counterparties (RBC, OCC) and for the hedge fund (Alyeska 5) but appears blank for some agent-block underlying clients (the IRT_TORG7C_FWD11 and TD MIDTERM NOTES PROGRAM entries on Zymer). This is more of a sparse-population issue than a total absence. | Identify which counterparty types are not getting industry classification. Likely the agent-underlying-client entities are being created without KYC industry classification — source from KYC.
11 | Tenor + Currency flattened into column names | The CCR Line Details has columns named "Min Availability 0 - 3 mo" / "Min Availability 3 - 12 mo" / "Min Availability 1 - 2 Yr" etc. — one column per (currency × tenor_bucket) combination | CCR Line Details on every counterparty page | Visible columns: Min Availability 0-3 mo, Min Availability 3-12 mo, Min Availability 1-2 Yr, Min Availability 2-5 Y. The Limit and Utilisation chart above shows CAD 0-3M, CAD 3M-1Y, CAD 1-2Y, CAD 2-5Y, CAD 5-10Y, CAD 10-50Y, CAD N-MTM, USD 0-3M, USD 3M-1Y, ... — 14 buckets (7 tenors × 2 currencies) | Ambiguous | Tenor bucket is properly a dimension but is being encoded as column suffix. Adding a new tenor bucket (e.g. an intraday daylight bucket) requires schema change. Filtering by tenor requires picking specific columns. | fact_limit_utilization with tenor_bucket_id and currency as proper dimensions, not column suffixes. R9.
12 | Source System dimension | Same logical product feeds from multiple source systems and the dashboard exposes the source codes raw | Across Trade Details panels | RBC trades: Source System = CALYPSO (for IRD trades and Commodity Forward); MUCM (for GOLD PHY). Alyeska trades: Source System = SOPHIS (for equity swaps), TCIM (for IM). Zymer trades: Source System = MANUAL. OCC: Source System = N/A (visible as literal text on every row). | Documented | Source system codes are visible to users (CALYPSO, MUCM, SOPHIS, TCIM, MANUAL, N/A) but they are infrastructure facts — users probably want product / asset class instead. "N/A" as a source system value is also worth flagging — there is a system; it just is not being captured for OCC. | Promote Source System to a proper dim_source_system. Separately, source product/asset class from the upstream system rather than letting source_system stand in for it. Investigate why OCC trades show N/A.
13 | Desk values | Desk encoded inconsistently — sometimes named, sometimes blank, sometimes embedded in Book name | RBC vs Alyeska vs Zymer vs OCC | RBC: Desk = IRD_NYK_NYSOFR, IRD_TOR_TOROPT, GOLD PHY. Alyeska: Desk = US PRIME EQ SWAP (4 rows) and IMDESK (IM row). Zymer: Desk = blank, blank, GED TDBLN EUCEDOPT, LME-AH, LME-AH. OCC: Desk = N/A for all rows. | Critical | Desk is a dimension but values include geographic codes (NYK, TOR), product codes (IRD, GOLD PHY, GED, LME-AH), counterparty types (IMDESK), and N/A. There is no consistent dimension. Several rows have Desk packed into the Book name with a MANUAL_ prefix. | Parse Desk into structured dim_desk with desk_code, desk_name, asset_class, location, parent_unit. Reconcile to the firms actual desk hierarchy. Investigate the N/A entries.
14 | Years To Maturity — derived field consistency | Same value repeated across rows that have different Trade and Maturity dates | OCC Trade Details (IMG_6257) | All 5 visible rows show Years To Maturity = 0.24658 despite different Trade Dates (20250917, 20251110, 20251110, 20251113, 20251113) and the same Maturity Date 20260805 | Ambiguous | Years To Maturity appears to be (Maturity Date - Value Date) / 365 — independent of Trade Date. The value 0.24658 = 90 days / 365 ≈ 0.247. Makes sense if all 5 trades mature at the same date and the Value Date is 20260507. But the column is labelled "Years To Maturity" not "Years From Value Date To Maturity" — these are equivalent only because Value Date is the snapshot date, not the trade booking date. | Document the calculation. Probably no fix needed but the column semantic should be explicit in the data dictionary.
15 | FX rates — %Change vs %D1D | Two columns of conceptually similar daily-change measures with different values and no semantic distinction | FX page FX Rate panel (IMG_6273) | For CAD: EOD_Rate=0.7335, IntrD_Rate=0.7303, %Change=-0.43%, %D1D=-0.11%, %W1W=-0.16%, %W2W=0.32%, %MoM=1.40%, %QoQ=-0.25%. The 0.43% gap matches (0.7303-0.7335)/0.7335 — so %Change = intraday vs prior EOD. But %D1D shows a different value (-0.11%) for the same currency same day. | Critical | Two columns measure superficially the same thing but yield different values. The model is opaque. %D1D likely = today EOD vs prior EOD (a closed-day comparison), while %Change = current intraday vs prior EOD (a still-moving day comparison). A user cannot tell. | Rename or document: column "Intraday Move (from prior EOD)" vs "Prior Day Closed Move". Or remove one if redundant. Either way, the panel needs a legend.
16 | BLOOMBERG_TICKER population | Tickers populated for some entities but "NOTICKER" or blank for others — same legal-name group | RBC Party Details (IMG_6255) vs RBC Capital Markets Agent (IMG_6256) | RBC entities: RB2C_LDN=2756Z LN, RBCM_LDN=2756Z LN, RB2C_SDY=69229Z AU. RBC Capital Markets agent entities: RBCQ_BSB and RBCQ_CAN both = NOTICKER. OCC entities (IMG_6257): all NOTICKER. Alyeska entities: NOTICKER. | Documented | Tickers are populated for entities that have a public listing (the LDN and SDY branches of RBC have Bloomberg identifiers). Private hedge funds (Alyeska), agent legal entities (RBC Capital Markets LLC), and clearing houses (OCC) genuinely do not have public tickers — hence NOTICKER. This is not a data gap, but the literal string "NOTICKER" is awkward. | Replace "NOTICKER" with NULL in dim_party. Add party_has_public_listing as a derived flag. Avoid magic strings as null indicators.
17 | Excess Flag breach rationale not surfaced | A breach can be caused by exposure growth (operational) or by limit reduction triggered by credit deterioration; the dashboard does not distinguish them | Zymer breach rows (IMG_6249) | CP_(TDSC)_(BAN2_EBL): Excess Flag=Y, Worst Rating=1A (high investment grade), Min Availability 3-12mo=-$700,081,641. CP_(TDBK)_(GAMP_C2C): Excess Flag=Y, Worst Rating=5C (very weak credit), Min Availability 0-3mo=-$364,084,371. | Ambiguous | The 1A breach is unusual — a high-quality client breaching is typically an operational/sizing issue. The 5C breach combines a breach with credit deterioration — much more urgent. Both render in the same pink shade with the same Y flag. The credit officer cannot rank by urgency from the breach surface alone. | Derive a breach_severity attribute: combines breach magnitude × counterparty rating tier × concentration. Surface as severity colour bands rather than binary Y/N.
18 | CPTY chart "X Lines Aggregated" headline can mismatch CCR Line Details rows shown | Chart and table disagree on how many lines are visible | RBC Legal Name View (IMG_6255 vs IMG_6248) | IMG_6255: Chart says "ROYAL BANK OF CANADA with 7 Lines Aggregated" but CCR Line Details below shows only 5 lines (CP_(TDBK)_(RBCD_DBL), CP_(TDBK)_(RBCM_DBL), CP_(TDBK)_(RBCV_C2C), CP_(TDBK)_(RBRL_DBL), CP_(TDBK)_(RRBB_DBL)). No HC_(TDBK)_(RBCM) row visible — but IMG_6248 (same counterparty, different navigation path) shows the HC line with the $8.96M dispute charge. | Critical | The same counterparty selection surfaces different sets of lines depending on how the user navigates to it. This is a transparency problem — the user cannot tell whether they are seeing a complete picture or a filtered subset. | The full line set per counterparty must be the default view, with explicit filters visible when narrowing. Audit the underlying query/filter logic to identify where the 2-line discrepancy comes from.
19 | Counterparty Code vs CP_CODE — two related identifiers | Two different fields, both representing counterparty identity, in different naming conventions | Across all Trade Details and Party Details panels | Trade Details has a column "Counterparty Code" containing values like CP_(TDBK)_(ALYA_C2C), CP_(TDBK)_(RBCM_C2C) — i.e. the line reference. Party Details has CP_CODE column with values like ALYA_C2C, ALYA_CYM, RBCM_LDN, RB2C_SDY — i.e. the counterparty entity code. | Ambiguous | Two related but distinct concepts share confusingly similar names. "Counterparty Code" is actually a line reference; "CP_CODE" is the party identifier. The names should be the other way around or, better, both renamed. | Rename: trade_details.counterparty_code → line_reference. party_details.CP_CODE → party_code. Document in glossary.
20 | IM row carries Maturity Date but no Trade Date | Some fields populated on IM rows, others blank — inconsistent | Alyeska IM row (IMG_6260) | IM row: Value Date=20260507, Book=TCIM_IMBOOK, Counterparty Code=CP_(TDBK)_(ALYA_C2C), Deal ID=USDCASH00006D1, Deal Type=IM, Desk=IMDESK, Trade Date=BLANK, Maturity Date=20261211, Source System=TCIM, Version=CRS3, Years To Maturity=0.59726, Deal M2M Currency=USD | Critical | Trade Date is blank for the IM row even though the row is a real booked entity. Maturity Date is populated — likely inherited from the underlying portfolio. Years To Maturity = 0.59726 matches the underlying Equity Swap rows above it (same value), so the IM row is showing the underlying portfolios maturity, not its own. The user cannot tell the IM rows own dates from the underlying portfolios dates. | Decide whether IM rows should carry: (a) their own dates (effective_date, maturity_date from CSA), or (b) the underlying portfolios dates (with underlying_portfolio_id pointer). Whichever way, do not silently inherit fields.
21 | Manual adjustment rows lose product information | Book name (MANUAL_LME-AH etc.) is the only place to find what was being adjusted | Zymer Trade Details (IMG_6249) | Manual adjustment rows: Book=MANUAL_ASG (×2), Book=MANUAL_GED TDBLN EUCEDOPT, Book=MANUAL_LME-AH (×2). Deal Type=Adjustment for all. Desk column is partially populated by parsing the Book name: ASG → ASG desk, GED TDBLN EUCEDOPT → GED TDBLN EUCEDOPT, LME-AH → LME-AH. | Critical | Adjustments to specific desks/portfolios are encoded into the Book name string and partially extracted into the Desk column. There is no link to which actual trades were adjusted. The product (the asset class being adjusted) is unknown — LME-AH suggests London Metal Exchange Aluminium-related, ASG could be Asset Servicing Group or similar, GED suggests some derivative type, but none of this is in proper dimensional fields. | Manual adjustment rows must carry: adjustment_reason_code, parent_trade_id (or parent_portfolio_id), originating_book, originating_desk. Parse the legacy MANUAL_* book names to populate these structured fields.
22 | INDUSTRY_RATING — meaning is unclear from data alone | Column is populated with single digits (3, 5) but the rating scale is not visible | RBC (3), Alyeska (5), OCC (3) | RBC is a bank (Canadian Schedule I) and gets INDUSTRY_RATING=3. OCC is a CCP (clearing house) and gets INDUSTRY_RATING=3. Alyeska is a hedge fund (multi-strategy) and gets INDUSTRY_RATING=5. | Ambiguous | INDUSTRY_RATING values 3 and 5 could mean different things — risk concentration tier, industry credit health, sub-sector code. The user cannot tell. The fact that two very different institutions (bank, CCP) get the same rating (3) is suspicious unless the scale is broad. | Document the INDUSTRY_RATING scale. If its a 1-5 risk tier scale, label it. If its an industry-sector classification code, replace numbers with sector labels. Add to glossary.